SANGAMON COUNTY ACTION TEAM

June 16, 2015 @ 12:00 PM

Sangamon County Courthouse

Meeting Minutes

Present:  Deanna Large, Pat Jacobs, Carly Mason, Ali Orr, Luann Gab, Christine Lindsey, Pat Kaidell, Angie Kramp, Raenesha Green, Leu Baker, Geneva Byrd, Kim Johnson

Social Service Fair:

- Vendors

  - 20 vendors have confirmed

  - Potential vendor list was reviewed to determine who has not replied

  - Agencies assigned to SCAT members to call and invite them to be vendors

  - Have all calls done by 6-30-15

  - Deanna will email a standard vendor letter; will change the reply date to 7-15-15

  - Deanna will send Ms. Baker the email from Janet Ulm so she can research who this is from District 186

  - Raenesha will check with 5th Street re: them being a vendor; they also have an HIV and STD testing mobile unit; Raenesha will check to see if they want to offer those services that day; if so, Deanna will check with Union Baptist to confirm their agreement to allow the mobile unit on the grounds

  - Ms. Baker will check with the Mosaic project about their interest in being a vendor

  - Christine indicated that many of the United Way members meet on a regular basis and many of them are on our vendor list; Deanna will email Christine the standard letter and she will forward it to that group to seek their participation

  - Deanna will email Pat K. the name of the program LLCC will be representing so that she knows who to contact at UIS

  - SCAT group members agree that we will move forward with the event with these 20 identified vendors; if we secure more vendors, then that just makes the event stronger

- Venue

  - Union Baptist Church

    - 1405 E. Monroe

    - Event will be 12-7

    - We can set up at 11 am

- Transportation

  - Still need an update from Cathi Marshall (did not address this issue at the 6-16-15 meeting)

- Funding

  - Shanelle continues to contact other businesses for donations

- Marketing

  - PSA’s are covered by Angie

  - DCFS Communications approved SCAT to have their own Facebook site; Angie will set the site up; Angie agreed to monitor the site

  - Flyer

    - Draft edited per members suggestions

    - Draft is attached for final review

    - Distribute the flyer in newsletters and website for high school and elementary school; have read during daily announcements; hard-copy to elementary schools, private schools, and daycare centers

- Incentives

  - Kathy has to wait one month before the event to contact PH and confirm the immunization mobile truck

  - We will have gift cards from Hyvee; maybe other donations

  - Welcome Bags

    - Primo $2/bag; just have to give them notice

    - Ms. Baker stated that the school district has a youth program that does screen printing; she will check on prices thru them

    - We will not worry about getting items to put in the bags when they get handed out

  - Latasha Roberson will make a donation from HP; she will get that to Deanna prior to the event

  - DCFS SFO has some gift baskets to donate; Gayle Hopper, Dave Schleyhahn, and Angie Kramp will prepare the baskets and bring to the event

- Steps to Monitor:

  - Solicitation of goods – Shanelle has the lead

  - PSA’s – Angie

  - Vendors – Ali, Twanya, Cathi, Deanna

  - Flyer – Deanna

  - Immunizations – Kathy

  - Welcome Bags – Judge Sanchez; Ms. Baker

SCAT Goals:

- Goals set will remain

- Data entry will continue

- Quarterly reporting will occur

NEXT SCAT MEETING:   July 15, 2015 at noon in Courtroom 7A