The Chicago North Action Team

Permanency Enhancement Initiative (PEI) Strategic Plan

Vision: Kids Staying With Their Families

Mission: To reduce the disproportionate number of African American youth in foster care through collaborative planning, community action, and policy advocacy.

Strategies:

1. Promote diverse stakeholder involvement in Chicago North Action Team (Outreach)

2. Provide practice recommendations to DCFS/ POS, Service Providers, and community-based orgs. in the Chicago North area

3. Provide education and training to Chicago North community stakeholders on disproportionality and cultural sensitivity

4. Identify programs/ services in the Chicago North area and determine their effectiveness

5. Increase child and family access to effective services in Chicago North

6. Provide recommendations for policy modifications to the PEI Transformation Team

Objectives:

Outreach

#1 – By December 2009, increase community involvement in Chicago North Action Team by 100%.

#2 – By December 2009, increase the number of caseworkers/ CPIs involved in the Chicago North Action Team by 4.

#3 – By March 2010, increase religious leader involvement in the Chicago North Action Team by 25%.

#4 – By March 2010, increase parent (DCFS/ Non-DCFS) involvement in the Chicago North Action Team by 50%.

#5 – By June 2010, increase the number of youth in care involved in the Chicago North Action Team by 3.

#6 – By September 2010, develop objectives, strategies, and action steps for the remaining 3 PEI Domains: Agency, Court, Service Provider

Education/ Training

#7 – By April 2010, develop and implement public education/ awareness plan for all Chicago North community stakeholders using all media forms.

Resource Assessment/ Development:

#8 – By December 2010, identify and evaluate the adequacy of existing community-based programs and services within the Chicago North area.

Action Plan (action steps)

Objective #1 – By December 2009 (March 2010), increase community  involvement in Chicago North Action Team by 100%.

Point Person- John Czarnecki (John.Czarnecki@illinois.gov)

| Action Step | Person(s) Responsible | Date Completed | Resources Required | Potential barriers or resistance | Collaborators |
| --- | --- | --- | --- | --- | --- |
| 1. Solicit/ Hold Meetings with Community Agencies | Jae, John, Robin | Completed as of 1.21.10 |  | Lack of Response No commitments yet Scheduling Conflicts | Albany Park CC, CPD CAP (23rd Dist.), Howard Area CC, Winfiend Moody, Alternatives, Children’s Memorial Hospital |
| 2. Continue to reach out to the community orgs | HACC: Donnis & Janea |  |  | Lack of resources at HACC* |  |
| 3. Gale Elementary– LSC meeting | Donnis | 4.13.10 | Needs updated brochure and flyers |  |  |
| 4. Resource Fair | Susan | 3.23.10 | Brochures and Flyers |  |  |
| 5. Hamdard Center | Jae | Completed Will check back in future months |  | They currently do not have staff available to attend |  |
| 6. Other (American Indian Center, Chicago Youth Programs, House of Good Sheppard) | John | Completed; f/u in future |  |  | Chicago Lakeshore Hospital, Streamwood BHS, JCFS, UCAN and Centro Romero 1) Haymarket Center 2) American Indian Center 3) Heartland Health Outreach 4) Alternatives |
| 7. Hold a training on strengthening families | Rosemary and Jackie | Defer until May 2010 for further discussion |  |  |  |

Regarding Step 7: we need to clarify the purpose of this training and whether it is an internal training or for community members as well.

Objective #2 – By December 2009, increase the number of caseworkers/ CPIs involved in the Chicago North Action Team by 4.

Point Person- Ralphael Longmire (Ralphael.Longmire@illinois.gov)

| Action Step | Person(s) Responsible | Date Completed | Resources Required | Potential barriers or resistance | Collaborators |
| --- | --- | --- | --- | --- | --- |
| 1. Contact CPI staff and invite to action team. | Ralphael Gloria Bean | January 21, 2010 / Partially Complete Recruitment ongoing |  | Scheduling challenges | Gloria Bean |
| 2. Develop a more specific strategy for how to engage these workers |  | May 2010 | - Create a message that ties the action team to their work; consider options like ad hoc committee or consultant status |  |  |

Objective #3 – By March 2010, increase religious leader involvement in the Chicago North Action Team by 25%.

Point Person- Susan Mellema (Susan.Mellema@illinois.gov)

| Action Step | Person(s) Responsible | Date Completed | Resources Required | Potential barriers or resistance | Collaborators |
| --- | --- | --- | --- | --- | --- |
| 1. Solicit/ Hold Meetings with Religious Leaders | Jennifer & Susan | January 30, 2010 February 5th, meeting will be rescheduled; complete by 4.15.10 |  | Lack of interest and/or response from religious leaders. | Pastor West United Church of Rogers Park |
| 2. Update flyer with new contact information | UIC (Kristen/ Julia) | Completed 2.18.10 |  |  |  |
| 3. Update brochure with new contact information | Susan | 4.5.10 |  |  |  |

Objective #4 – By March 2010, increase parent (DCFS/ Non-DCFS) involvement in the Chicago North Action Team by 50%.

Point Person-

| Action Step | Person(s) Responsible | Date Completed | Resources Required | Potential barriers or resistance | Collaborators |
| --- | --- | --- | --- | --- | --- |
| 1. Present action team mission and vision to Birth Parent Council | Robin, Sue | February 18, 2010 --- Deferred to June 2010 |  | Scheduling & Birth Parent Council in area no longer active | Donella Bishop & Marsha Harris |
| 2. Review C-4 Parent Education schedule and identify potential action team presentation dates. | Jae | December 17, 2009/ Completed |  |  |  |
| 3. Attend parent Education meeting. | Jae | February 1, 2010 Deferred to April 15, 2010 |  | Scheduling barriers |  |
| 4. Identify parents and workers to attend team meetings together | Susan Ralphael | June 1, 2010 | Flyers | Scheduling |  |
| 5. Identify non-DCFS involved parents (Strengthening Families/ Parent Cafes) | Jackie Rivers | June 1, 2010 | Flyers | Scheduling |  |

Objective #5 – By June 2010, increase the number of youth in care involved in the Chicago North Action Team by 3.

| Action Step | Person(s) Responsible | Date Completed | Resources Required | Potential barriers or resistance | Collaborators |
| --- | --- | --- | --- | --- | --- |

Objective #6 – By September 2010, develop objectives, strategies, and action steps for the remaining 3 PEI Domains: Agency, Court, Service Provider

| Action Step | Person(s) Responsible | Date Completed | Resources Required | Potential barriers or resistance | Collaborators |
| --- | --- | --- | --- | --- | --- |

Objective #7 – By July 2010, develop and implement public education/ awareness plan for all Chicago North community stakeholders using all media forms

Point Person- Jennifer Caruso (Jennifer@rogerspark.org)

| Action Step | Person(s) Responsible | Date Completed | Resources Required | Potential barriers or resistance | Collaborators |
| --- | --- | --- | --- | --- | --- |
| 1. Identify communications expert (including Interns) | Jennifer& Julia | January 21, 2010 Loyola communication completed Deferred to ? | Intern Supervisor | School schedule & Requires supervision of intern UIC Communications department is small and oversight recently delegated to new department (LAS) | Chris Skagle (Loyola University) Robin Hurst/ UIC – Office of Library Science (LAS) might be able to add DCFS to web portal Meanwhile, Professor Barnhardt (UIC Communications) will attempt to locate a graduate intern |
| 2. Identify the audiences that will be targeted. | Jae, Sandra Jennifer, Intern, Gloria | Completed 2.26.10 |  | Holiday Schedule |  |
| 3. Contact DCFS Communications person regarding intern supervision | Sue, Ralphael, Gloria Bean | January 21, 2010 Completed |  | Scheduling conflicts | Bridgette Glickman (DCFS) |
| 4. Develop a media plan that identifies all community based media streams | Sue, Ralphael, Intern | March 18, 2010 Deferred July 1, 2010 |  | DCFS policy Assumes that the first 3 steps are completed. | Bridgette Glickman (DCFS) or someone she assigned. Cathie Bazzon, Rogers Park Community Council |
| 5. Speak with DCFS Communications Dept about whether they have a staff who can assist the action team in developing the public education plan | Gloria |  |  |  |  |

Objective #8 – By December 2010, identify and evaluate the adequacy of existing community-based programs and services within the Chicago North area.

Point Person- Jenetia Marshall (Jemarch@cookcountygov.com)

| Action Step | Person(s) Responsible | Date Completed | Resources Required | Potential barriers or resistance | Collaborators |
| --- | --- | --- | --- | --- | --- |
| 1. Invite Dana Weiner of the Geo Map Data base for action team training. | John | January 21, 2010 / Completed |  | Scheduling Conflicts | Dana Weiner |
| 2. Identify or Develop a family needs assessment tool. | Donnella Ward Susan Mellema Jenetia Marshall John | March 1, 2010 Completed the identification aspect of this step; will refine the tool for our needs on April 15, 2010 |  | Getting a DCP person on the Action Team. Getting consistent participation POS and DCFS accessibility and lack of use | Differential Response Teams (DCFS) DCP Supervisor or workers Jeffrey Walker, ACR |
| 3. Assess and/or Conduct focus groups with community stakeholders to identify needs | Robin, Donnis & John | June 30, 2010 |  |  | Cook South Action Team questionnaire / results Donnella Bishop-Ward Pre-symposium Community Forums |

Input for the Chicago North Action Team Vision, Mission, & Objectives provided by the following team members:

- Barbara Burnett, DCFS

- Donnella Bishop, Birth Parent Council

- Donnis Briscoe, DCFS

- Iris Cuevas, DCFS

- Jae Jin Pak, C-4

- Jenetia Marshall, GAL

- Jennifer Caruso, Rogers Park Community Council

- John Czarnecki, DCFS

- Russ Hopkins, National Military Family Association

- Ralphael Longmire, DCFS

- Robin Robinson, DCFS

- Nathan Rosato, Lawrence Hall Youth Services

- Susan Mellema, DCF

	Alan Dettlaff, UIC