The 1911 Action Team

Permanency Enhancement Initiative (PEI) Strategic Plan

(Developed February 18, 2010 – Beatrice Caffrey)

Vision: Restoring Families, Rebuilding Communities

Mission: To build and restore communities by providing supportive services to families that educate, stabilize and empower.

Objectives:

Outreach

(	#1 – By May 2010, implement a town hall meeting that occurs semi-annually

(	#2 – By April 2010, get active parents on the action team.

Education/ Training

(	#3 – By January 2011, develop and implement Parent Cafes

Resource Assessment/ Development:

(	#4 – By February 2010, develop working committees to carry out various team strategies

Strategies:

1. Promote diverse stakeholder involvement in 1911 Action Team (Outreach).

2. Provide education and training to parents on strengthening families.

3. Provide education and training to community stakeholders on disproportionality and cultural sensitivity.

Action Plan (action steps)

Objective #1 – By May 2010, implement a townhall meeting that occurs semi-annually.

| Action Step | Person(s) Responsible | Date Completed | Resources Required | Potential barriers or resistance | Collaborators |
| --- | --- | --- | --- | --- | --- |
| 1. Determine logistics (speaker, agenda, $, location, date) | Committee members (Derrick, Jenetia, Sherri, Martha and Jackie | Completed 6/23/10 | Kismet will cover costs and host the event; Date is 6/23 from 6-8 pm | Funding and finding a location | Ask the LAN if they can co-sponsor with the Action Team |
| 2. Outreach/PR | Everyone will help with this task; Martha will post it on the website | Completed | Media/PR materials |  |  |
| 3. Visit another townhall meeting | Jackie will find out upcoming dates; representatives from the committee will attend; Russ will send out dates for the upcoming Niles West HS townhall | March 1 April 1 |  | There may not be one scheduled within our time frame | LAN 63; Niles Township Youth Council |
| 4. Research need of community (LANS 76 & 80) | Sherri | By next meeting | Survey Report |  |  |

Objective #2 – By April 2010, get active parents on the action team.

| Action Step | Person(s) Responsible | Date Completed | Resources Required | Potential barriers or resistance | Collaborators |
| --- | --- | --- | --- | --- | --- |
| 1. Visit Schools (Local School Councils and Report Card Distribution) | Lucille, Bobbie, Rhegea | Completed April 2010 | - PR Materials to hand out about action team (Flyer, sign-up sheet, outreach letter) |  | Reavis High School; Chicago Vocational HS; DuSable or King HS |
| 2. Send materials to churches within LANS (utilize the foster parent list) | Lucille and Jackie | Completed May 2010 |  | Must check with the DCFS Communications Dept before mailing materials out |  |
| 3. Contact Public Defenders Office | Jenetia and Faith | In process |  |  |  |
| 4. Send a brochure and flyer to parents on case load | Rhegea and Bobbie | Completed |  |  |  |
| 5. Distribute action team info at ACR, Court and CAYIT | Martha | Defer until further notice |  | Cost of flyers |  |
| 6. Attend Parent advisory and PIP program | Jackie will research Lucille and Martha spoke with Donella Bishop Ward | Completed 2.25.10; further follow up needed in future |  |  |  |
| 7. Resource Fair |  | June 2011 |  |  |  |
| 8. Get date and time of DCFS Youth Summit | Lucille | Completed |  |  |  |

Objective #3 – By January 2011, develop and implement Parent Cafes.

| Action Step | Person(s) Responsible | Date Completed | Resources Required | Potential barriers or resistance | Collaborators |
| --- | --- | --- | --- | --- | --- |
| 1. Research history of development of SFI | Beverly | June 2010 Completed |  |  | Chris McGrath |
| 2. Visit Strengthening Families Parent Cafes | Martha and Sherri Martha, Marcia, Bobbie and Rhegea | Completed Nov. 2010 |  |  |  |
| 3. Invite SFI parents to present to the action team | Jackie | June 30, 2010 Completed |  | Scheduling may be a challange |  |
| 4. Get parents from the Action Team trained as leaders of the Parent Cafes | Parent Committee | October 2010 |  |  |  |
| 5. Determine logistics for the parent cafes (venues, dates, presenters, etc.) |  | January 2011 |  | Potential fee for technical assistance from SFI | LAN |

Objective #4 – By February 2010, develop working committees to carry out various team strategies.

| Action Step | Person(s) Responsible | Date Completed | Resources Required | Potential barriers or resistance | Collaborators |
| --- | --- | --- | --- | --- | --- |
| 1. Develop committees | All | Completed 2.18.10 |  |  |  |

Input for the Chicago North Action Team VMOSA provided by the following team members:

- Martha Saines, DCFS

- Derrick Faulkner, Kismet

- Marcia Williams, DCFS

- Jackie Rivers, DCFS

- Lucille Pearson, DCFS

- Bobbie Logan, CCCS

- Rhegea Tate, Beatrice Caffrey

- Jenetia Marshall, GAL

- Faith Seals, DCFS

- Anika Todd, DCFS

- Beverly Mims, DCFS

- Carol Jones, DCFS

- Lorne Garrett, DCFS

- Marcia Weflen, LSSI

- Russ Hopkins, NMFA